## Dashboard
Please Select a Project to View Related Tasks |  |  | 4 |  | All Projects | 80 Tasks Found | [6 empty] | Gantt. Scroll | [6 empty] | 0
Dashboard |  |  |  | Task ID | Top Tasks | Responsible | Start Date | End Date | Days Req. | Status | Days Comp. | Project | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06
|  |  | 0 | 0 | 0 | 1 | 2 | 4 | 3 | 4 |  | -1
|  |  |  | 1 | Project 1 - Task 1 | Person 1 | 2024-02-24 | 2024-02-28 | 5 | 100% | 5 | Project 1
| Overall Progress |  |  | 2 | Project 3 - Task 1 | Person 2 | 2024-02-25 | 2024-03-01 | 6 | 100% | 6 | Project 3
|  |  |  | 3 | Project 1 - Task 2 | Person 3 | 2024-02-26 | 2024-03-06 | 10 | 100% | 10 | Project 1
|  |  |  | 4 | Project 1 - Task 3 | Person 4 | 2024-03-01 | 2024-03-09 | 9 | 100% | 9 | Project 1
|  |  |  | 5 | Project 1 - Task 4 | Person 5 | 2024-02-25 | 2024-02-28 | 4 | 100% | 4 | Project 1
|  |  |  | 6 | Project 1 - Task 5 | Person 1 | 2024-02-28 | 2024-03-04 | 6 | 100% | 6 | Project 1
| Start Date | 2024-02-20 |  | 7 | Project 1 - Task 6 | Person 2 | 2024-02-28 | 2024-03-05 | 7 | 100% | 7 | Project 1
| End Date | 2024-03-21 |  | 8 | Project 1 - Task 7 | Person 3 | 2024-03-02 | 2024-03-06 | 5 | 100% | 5 | Project 1
| Overall Progress | 55.08% |  | 9 | Project 1 - Task 8 | Person 4 | 2024-03-02 | 2024-03-10 | 9 | 100% | 9 | Project 1
|  | 44.92% |  | 10 | Project 1 - Task 9 | Person 5 | 2024-03-03 | 2024-03-08 | 6 | 100% | 6 | Project 1
| Days Required | 30 days |  | 11 | Project 2 - Task 1 | Person 1 | 2024-02-21 | 2024-02-26 | 6 | 59% | 3.54 | Project 2
|  | 529 man-days |  | 12 | Project 2 - Task 2 | Person 2 | 2024-02-25 | 2024-03-04 | 9 | 41% | 3.69 | Project 2
|  |  |  | 13 | Project 2 - Task 3 | Person 3 | 2024-02-26 | 2024-03-04 | 8 | 0% | 0 | Project 2
|  |  |  | 14 | Project 2 - Task 4 | Person 4 | 2024-02-28 | 2024-03-05 | 7 | 49% | 3.43 | Project 2
| Total Tasks | 80 |  | 15 | Project 2 - Task 5 | Person 5 | 2024-03-01 | 2024-03-04 | 4 | 36% | 1.44 | Project 2
| Not Started(0%) | 2 |  | 16 | Project 2 - Task 6 | Person 1 | 2024-03-01 | 2024-03-06 | 6 | 54% | 3.24 | Project 2
| Inprogress(1-99%) | 58 |  | 17 | Project 2 - Task 7 | Person 2 | 2024-03-04 | 2024-03-09 | 6 | 57% | 3.42 | Project 2
| 1-25% | 11 |  | 18 | Project 2 - Task 8 | Person 3 | 2024-03-05 | 2024-03-08 | 4 | 22% | 0.88 | Project 2
| 26-50% | 30 |  | 19 | Project 2 - Task 9 | Person 4 | 2024-03-07 | 2024-03-13 | 7 | 46% | 3.22 | Project 2
| 51-75% | 15 |  | 20 | Project 2 - Task 10 | Person 5 | 2024-02-24 | 2024-02-26 | 3 | 100% | 3 | Project 2
| 76-99% | 2 |  | 21 | Project 3 - Task 2 | Person 1 | 2024-02-20 | 2024-02-29 | 10 | 100% | 10 | Project 3
| Completed(100%) | 20 |  | 22 | Project 3 - Task 3 | Person 2 | 2024-03-01 | 2024-03-05 | 5 | 100% | 5 | Project 3
|  |  |  | 23 | Project 3 - Task 4 | Person 3 | 2024-03-03 | 2024-03-09 | 7 | 100% | 7 | Project 3
|  |  |  | 24 | Project 3 - Task 5 | Person 4 | 2024-03-06 | 2024-03-12 | 7 | 100% | 7 | Project 3
|  |  |  | 25 | Project 3 - Task 6 | Person 5 | 2024-03-08 | 2024-03-10 | 3 | 100% | 3 | Project 3
Please let us know your feedback ¦ Email: rajeswaranm2003@gmail.com
55%

## Projects Summary
Project Management
Projects | Tasks | Start | End | Days | %Progress | Remaining
All Projects | 80 | 2024-02-20 | 2024-03-21 | 529 | 55.08% | 44.92%
Project 1 | 9 | 2024-02-24 | 2024-03-13 | 61 | 100% | 0%
Project 2 | 10 | 2024-02-21 | 2024-03-16 | 60 | 46.4% | 53.6%
Project 3 | 6 | 2024-02-20 | 2024-03-18 | 38 | 100% | 0%
Project 4 | 7 | 2024-02-24 | 2024-03-21 | 51 | 44.43% | 55.57%
Project 5 | 8 | 2024-02-27 | 2024-03-20 | 55 | 33.88% | 66.12%
Project 6 | 8 | 2024-02-24 | 2024-03-12 | 52 | 63% | 37%
Project 7 | 9 | 2024-02-21 | 2024-03-13 | 62 | 40.56% | 59.44%
Project 8 | 11 | 2024-02-20 | 2024-03-21 | 69 | 47.91% | 52.09%
Project 9 | 4 | 2024-02-27 | 2024-03-15 | 26 | 48.25% | 51.75%
Project 10 | 8 | 2024-02-27 | 2024-03-20 | 55 | 33.88% | 66.12%
Formulas:
Start = MIN(Table1[Start Date])
Start = MIN(IF(Table1[Project]=[Projects],Table1[Start Date]))
End = MAX(Table1[Start Date])+MAX(Table1[Days Req.])
End = MAX(IF(Table1[Project]=[Projects],Table1[Start Date]))+MAX(IF(Table1[Project]=[Projects],Table1[Days Req.]))
1.
Input Your Project Title Here

## Data Sheet
Project | Task | Responsible | Start Date | Days Req. | Progress
Project 1 | Project 1 - Task 1 | Person 1 | 2024-02-24 | 5 | 100%
Project 3 | Project 3 - Task 1 | Person 2 | 2024-02-25 | 6 | 100%
Project 1 | Project 1 - Task 2 | Person 3 | 2024-02-26 | 10 | 100%
Project 1 | Project 1 - Task 3 | Person 4 | 2024-03-01 | 9 | 100%
Project 1 | Project 1 - Task 4 | Person 5 | 2024-02-25 | 4 | 100%
Project 1 | Project 1 - Task 5 | Person 1 | 2024-02-28 | 6 | 100%
Project 1 | Project 1 - Task 6 | Person 2 | 2024-02-28 | 7 | 100%
Project 1 | Project 1 - Task 7 | Person 3 | 2024-03-02 | 5 | 100%
Project 1 | Project 1 - Task 8 | Person 4 | 2024-03-02 | 9 | 100%
Project 1 | Project 1 - Task 9 | Person 5 | 2024-03-03 | 6 | 100%
Project 2 | Project 2 - Task 1 | Person 1 | 2024-02-21 | 6 | 59%
Project 2 | Project 2 - Task 2 | Person 2 | 2024-02-25 | 9 | 41%
Project 2 | Project 2 - Task 3 | Person 3 | 2024-02-26 | 8 | 0%
Project 2 | Project 2 - Task 4 | Person 4 | 2024-02-28 | 7 | 49%
Project 2 | Project 2 - Task 5 | Person 5 | 2024-03-01 | 4 | 36%
Project 2 | Project 2 - Task 6 | Person 1 | 2024-03-01 | 6 | 54%
Project 2 | Project 2 - Task 7 | Person 2 | 2024-03-04 | 6 | 57%
Project 2 | Project 2 - Task 8 | Person 3 | 2024-03-05 | 4 | 22%
Project 2 | Project 2 - Task 9 | Person 4 | 2024-03-07 | 7 | 46%
Project 2 | Project 2 - Task 10 | Person 5 | 2024-02-24 | 3 | 100%
Project 3 | Project 3 - Task 2 | Person 1 | 2024-02-20 | 10 | 100%
Project 3 | Project 3 - Task 3 | Person 2 | 2024-03-01 | 5 | 100%
Project 3 | Project 3 - Task 4 | Person 3 | 2024-03-03 | 7 | 100%
Project 3 | Project 3 - Task 5 | Person 4 | 2024-03-06 | 7 | 100%
Project 3 | Project 3 - Task 6 | Person 5 | 2024-03-08 | 3 | 100%
Project 4 | Project 4 - Task 1 | Person 1 | 2024-03-10 | 9 | 88%
Project 4 | Project 4 - Task 2 | Person 2 | 2024-03-11 | 10 | 20%
Project 4 | Project 4 - Task 3 | Person 3 | 2024-02-24 | 4 | 10%
Project 4 | Project 4 - Task 4 | Person 4 | 2024-02-27 | 8 | 60%
Project 4 | Project 4 - Task 5 | Person 5 | 2024-03-02 | 10 | 34%
Project 4 | Project 4 - Task 6 | Person 1 | 2024-03-05 | 6 | 51%
Project 4 | Project 4 - Task 7 | Person 2 | 2024-03-05 | 4 | 48%
Project 5 | Project 5 - Task 1 | Person 3 | 2024-03-08 | 8 | 32%
Project 5 | Project 5 - Task 2 | Person 4 | 2024-03-10 | 9 | 42%
Project 5 | Project 5 - Task 3 | Person 5 | 2024-02-28 | 5 | 59%
Project 5 | Project 5 - Task 4 | Person 1 | 2024-02-27 | 3 | 31%
Project 5 | Project 5 - Task 5 | Person 2 | 2024-03-01 | 7 | 49%
Project 5 | Project 5 - Task 6 | Person 3 | 2024-03-02 | 10 | 16%
Project 5 | Project 5 - Task 7 | Person 4 | 2024-03-02 | 10 | 31%
Project 5 | Project 5 - Task 8 | Person 5 | 2024-03-02 | 3 | 11%
Project 6 | Project 6 - Task 1 | Person 1 | 2024-02-24 | 5 | 47%
Project 6 | Project 6 - Task 2 | Person 2 | 2024-02-25 | 6 | 43%
Project 6 | Project 6 - Task 3 | Person 3 | 2024-02-26 | 10 | 38%
Project 6 | Project 6 - Task 4 | Person 4 | 2024-03-01 | 9 | 100%
Project 6 | Project 6 - Task 5 | Person 5 | 2024-02-25 | 4 | 100%
Project 6 | Project 6 - Task 6 | Person 1 | 2024-02-28 | 6 | 100%
Project 6 | Project 6 - Task 7 | Person 2 | 2024-02-28 | 7 | 42%
Project 6 | Project 6 - Task 8 | Person 3 | 2024-03-02 | 5 | 34%
Project 7 | Project 7 - Task 1 | Person 4 | 2024-03-02 | 9 | 14%
Project 7 | Project 7 - Task 2 | Person 5 | 2024-03-03 | 6 | 55%
Project 7 | Project 7 - Task 3 | Person 1 | 2024-02-21 | 7 | 59%
Project 7 | Project 7 - Task 4 | Person 2 | 2024-02-25 | 9 | 41%
Project 7 | Project 7 - Task 5 | Person 3 | 2024-02-26 | 8 | 0%
Project 7 | Project 7 - Task 6 | Person 4 | 2024-02-28 | 7 | 49%
Project 7 | Project 7 - Task 7 | Person 5 | 2024-03-01 | 4 | 36%
Project 7 | Project 7 - Task 8 | Person 1 | 2024-03-01 | 6 | 54%
Project 7 | Project 7 - Task 9 | Person 2 | 2024-03-04 | 6 | 57%
Project 8 | Project 8 - Task 1 | Person 3 | 2024-03-05 | 4 | 22%
Project 8 | Project 8 - Task 2 | Person 4 | 2024-03-07 | 7 | 46%
Project 8 | Project 8 - Task 3 | Person 5 | 2024-02-24 | 3 | 100%
Project 8 | Project 8 - Task 4 | Person 1 | 2024-02-20 | 10 | 47%
Project 8 | Project 8 - Task 5 | Person 2 | 2024-03-01 | 5 | 55%
Project 8 | Project 8 - Task 6 | Person 3 | 2024-03-03 | 7 | 38%
Project 8 | Project 8 - Task 7 | Person 4 | 2024-03-06 | 7 | 33%
Project 8 | Project 8 - Task 8 | Person 5 | 2024-03-08 | 3 | 68%
Project 8 | Project 8 - Task 9 | Person 1 | 2024-03-10 | 9 | 88%
Project 8 | Project 8 - Task 10 | Person 2 | 2024-03-11 | 10 | 20%
Project 8 | Project 8 - Task 11 | Person 3 | 2024-02-24 | 4 | 10%
Project 9 | Project 9 - Task 1 | Person 4 | 2024-02-27 | 8 | 60%
Project 9 | Project 9 - Task 2 | Person 5 | 2024-03-02 | 10 | 34%
Project 9 | Project 9 - Task 3 | Person 1 | 2024-03-05 | 6 | 51%
Project 9 | Project 9 - Task 4 | Person 2 | 2024-03-05 | 2 | 48%
Project 10 | Project 10 - Task 1 | Person 3 | 2024-03-08 | 8 | 32%
Project 10 | Project 10 - Task 2 | Person 4 | 2024-03-10 | 9 | 42%
Project 10 | Project 10 - Task 3 | Person 5 | 2024-02-28 | 5 | 59%
Project 10 | Project 10 - Task 4 | Person 1 | 2024-02-27 | 3 | 31%
Project 10 | Project 10 - Task 5 | Person 2 | 2024-03-01 | 7 | 49%
Project 10 | Project 10 - Task 6 | Person 3 | 2024-03-02 | 10 | 16%
Project 10 | Project 10 - Task 7 | Person 4 | 2024-03-02 | 10 | 31%
Project 10 | Project 10 - Task 8 | Person 5 | 2024-03-02 | 3 | 11%
2.
Input Your Tasks of Your Project and Respective Timelines